## RAID LOG
| RAID Log | Should you face any difficulty in completing the RAID Log, please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | [6 empty] | Total | Critical | High | Moderate | Low | Negligible
| Project title: | IAC Community Ambassador Onboarding & UTM Tracking System |  | Project Id: |  | Project Manager: | Harshada Topale
| DOCUMENT VERSION: | 1 |  | Last Updated date: | 2025-04-20 | Project Team Lead: | NA
| Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed
| RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
1 | Risk | Difficulty integrating JavaMail API for sending real emails. | Could delay onboarding email feature, affecting project timeline. | Refer to JavaMail docs, test with simulation first, get mentor support. | Rashmi Sahani | Moderate | 3 | Open
2 | Assumption | Java and MySQL will be installed and configured correctly. | If not available, it could delay setup and development. | Include environment setup in checklist and test on Day 1. | Rashmi Sahani | Low | – | Closed
3 | Issue | CSV export doesn't handle special characters or large text. | May result in incomplete or unreadable exported files. | Use UTF-8 encoding and sanitize input strings. | Rashmi Sahani | Moderate | 2 | Open
4 | Dependency | Gmail SMTP App Password required for email delivery. | Real email feature won't work without it. | Use simulated email until access is configured; request credentials early. | Rashmi Sahani | High | 4 | Open
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24