## Project Schedule
IAC Internship Progra 2023 - Java Project Schedule
|  | PROJECT START DATE | 2025-02-27
|  | Display Week Sr No | 1 | [10 empty] | 2025-02-24 | [6 empty] | 2025-03-03 | [6 empty] | 2025-03-10 | [6 empty] | 2025-03-17 | [6 empty] | 2025-03-24 | [6 empty] | 2025-03-31 | [6 empty] | 2025-04-07 | [6 empty] | 2025-04-14 | [6 empty] | 2025-04-21
Should you face any difficulty in completing the 'Project Schedule', please refer to 'Project Planning' Workshop, https://cloudcounselage.graphy.com/sessions/Project-Planning-64af88dcb308530823e2c19f | time axis 2025-02-24 to 2025-04-27
Sr No | Week/ Duration/ Sprint/ Phase | Activities | Task | Sub Task | Dependencies | Assigned to | Start Date | End Date | End Date | Hours required | Status | Progress | Comments | time axis 2025-02-24 to 2025-04-27
1 | Week 1 | Initiation Phase |  |  |  |  | 2025-02-27 |  | 2025-03-03 |  | Completed | 100% | Initial setup
1.1 |  | Requirement Gathering |  |  |  |  | 2025-02-27 | 2023-08-05 | 2025-02-28 | 4 | Completed | 100% | Reviewed problem
1.1.1 |  | Study Problem |  |  |  |  | 2025-02-27 |  | 2025-02-27 | 2 | Completed | 100% | Studied brief
1.1.2 |  | Analyze Tools |  | Java, JDBC, JavaMail |  |  | 2025-02-28 |  | 2025-02-28 | 2 | Completed | 100% | Confirmed tools
1.1.3 |  | Mentor Discussion |  | Clarify doubts |  |  | 2025-02-28 |  | 2025-02-28 | 1 | Completed | 100% | Mentor clarifications
1.1.4 |  | Setup DB Schema |  | MySQL Schema Design |  |  | 2025-03-01 |  | 2025-03-01 | 1 | Completed | 100% | Schema done
1.2 |  | Planning |  |  |  |  | 2025-03-02 |  | 2025-03-04 | 4 | Completed | 100% | Planning ongoing
1.2.1 |  | Design Flow |  | Flow Diagram |  |  | 2025-03-02 |  | 2025-03-03 | 3 | Completed | 100% | Flow rough draft
1.2.1.1 |  | Define Key Modules |  | Submodules | 1.2.1 |  | 2025-03-03 |  | 2025-03-03 | 1 | Completed | 100% | Working on modules
1.2.3 |  | Set Milestones |  |  |  |  | 2025-03-03 |  | 2025-03-04 | 2 | Completed | 100% | Fnalized
2 | Week 2 | Development Phase |  |  |  |  | 2025-03-04 |  | 2025-03-09 |  | Completed | 100% | Start coding next
2.1 |  | UTM Module |  |  |  |  | 2025-03-04 |  | 2025-03-05 | 4 | Completed | 100% | Build UTM logic

## SHEET 1
PROJECT PLAN
DOCUMENT VERSION: 1.0
PROJECT NAME | IAC Community Ambassador Onboarding System
PROJECT MANAGER | Harshada Topale
PROJECT DELIVERABLE | UTM Generator App, Ambassador DB, Welcome Email System
PROJECT SCOPE | Automate CA onboarding, generate UTM links, store data, and track ambassador activities
PROJECT START DATE | 2025-02-27
PROJECT END DATE | 2025-03-23
OVERALL PROGRESS | Completed
SL NO | TASK NAME | ASSIGNED TO | START DATE | END DATE | DURATION IN DAYS | STATUS
| 1 Initiation | Rashmi | 2025-02-27 | 2025-03-01 | 3 | COMPLETED
| 1.1 Understand Problem Statement | Rashmi | 2025-02-27 | 2025-02-27 | 1 | COMPLETED
| 1.2 Identify Tech Stack | Rashmi | 2025-02-28 | 2025-02-28 | 1 | COMPLETED
| 1.3 Setup Local Environment | Rashmi | 2025-03-01 | 2025-03-01 | 1 | COMPLETED
| 2 Planning | Rashmi | 2025-03-02 | 2025-03-04 | 3 | COMPLETED
| 2.1 Design Workflow & DB Schema | Rashmi | 2025-03-02 | 2025-03-03 | 2 | COMPLETED
| 2.2 Define Modules & Features | Rashmi | 2025-03-03 | 2025-03-04 | 2 | COMPLETED
| 3 Execution | Rashmi | 2025-03-05 | 2025-03-16 | 12 | IN PROGRESS
| 3.1 UTM Generator Module | Rashmi | 2025-03-05 | 2025-03-06 | 2 | COMPLETED
| 3.2 MySQL JDBC Integration | Rashmi | 2025-03-07 | 2025-03-08 | 2 | COMPLETED
| 3.3 Email Sender (JavaMail) | Rashmi | 2025-03-09 | 2025-03-10 | 2 | COMPLETED
| 3.4 View/Search Feature | Rashmi | 2025-03-11 | 2025-03-11 | 1 | COMPLETED
| 3.5 Update/Delete Ambassador | Rashmi | 2025-03-12 | 2025-03-12 | 1 | COMPLETED
| 3.6 Export to CSV | Rashmi | 2025-03-13 | 2025-03-13 | 1 | COMPLETED
| 3.7 Total Count Feature | Rashmi | 2025-03-14 | 2025-03-14 | 1 | COMPLETED
| 3.8 Dashboard Enhancements | Rashmi | 2025-03-15 | 2025-03-15 | 1 | IN PROGRESS
| 3.9 Real Email via SMTP App Pass | Rashmi | 2025-03-16 | 2025-03-16 | 1 | COMPLETED
| 4 Testing | Rashmi | 2025-03-17 | 2025-03-20 | 4 | COMPLETED
| 4.1 Manual Testing | Rashmi | 2025-03-17 | 2025-03-18 | 2 | COMPLETED
| 4.2 Test Plan + Bug Fixes | Rashmi | 2025-03-19 | 2025-03-20 | 2 | COMPLETED
| 5 Closure | Rashmi | 2025-03-21 | 2025-03-23 | 3 | COMPLETED
| 5.1 Final Report & Docs | Rashmi | 2025-03-21 | 2025-03-22 | 2 | COMPLETED
| 5.2 Video Demo + Submission | Rashmi | 2025-03-23 | 2025-03-23 | 1 | COMPLETED